## Slide 1: Status

## Slide 2: Project Status – March 25 II. Data Ingestion and Cleaning/Wrangling
Blocked
Understand HPLC Data Collection: Data collection process to generate HPLC? How much spread in SHU is expected for 1 genotype?
To Do
Read in LICOR data from all different formats
Clean LICOR Data
Add addition columns to LICOR and perform feature analysis
Combine LICOR with SHU and Visualize data
Completed
Setup GIT for project
Create excel file of HPLC data, add gbs/names, and then read into excel
Clean data: standardize column types, handle ”<“ , add shu labels
Plot hplc data, look for outliers/important behavior
In Progress
Design interactive app to look at the data - Build interactive app interface - Graphs of SHU per genotype - Anomaly/outlier graphs
Work with Ibrar and team to create standardized LICOR input for R Code

## Slide 3: Project Status – April 15 II. Data Ingestion and Cleaning/Wrangling
Blocked
Understand how to handle missing rep in LICOR data at Leyendecker
To Do
Completed
Read in and clean LICOR data from all different formats
Read in and clean/wrangle the harvest data
Combine data all sources
In Progress
Design interactive app to look at the data - Build interactive app interface ✅ Add SHU tab ✅ Add licor tab Add harvest tab Combination/analysis
Perform Feature analysis on data, and get initial results Correlation between SHU and licor features Look for predictive trends between harvest and stress factors
Work with Ibrar and team to create standardized LICOR input for R Code