## Slide 1: LICOR Project
Chile Team
Lily Northcutt

## Slide 2: Outline
Goals and Motivation
Data: collection process, and description of out data sources
Possible Roadblocks/Risks and Mitigation
Project Task Outline/Progress Check

## Slide 3: Goals and Motivation
Goal
  Understand the relationship between the HPLC and porometry/fluorometry, which factors are most influential, and by how much.
  We will do this by training a model to predict HPLC using the porometry/fluorometry data – all collected for 20 genotypes at Leyendecker and FG.
Motivation
  Plant breeders and researchers want to understand the relationship between stress and HPLC in peppers because it will help them with breeding/growing peppers with SHU requirements.

## Slide 4: Data (1/2): Collection Process LICOR
2. Five plants are sampled from each replication
1. Each genotype is planted in 3 replications
3. Location dependent, n number of readings are taken from each sampled plant
FG – 3 readings / plant
Ley – 1 reading / plant

## Slide 5: Data (2/2): Data Sources
1. HPLC Data
  File 1: PDF with HPLC data for Leyendecker
  File 2: PDF with HPLC data for FG
  Note: 1 data point per GBS, i.e. all 15 plants in each replication (45 in total) were combined
2. Porometry/Fluorometry Data (LICOR)
  File 3: FG readings (45 per genotype) taken on 9/4/23
  File 4: Ley readings (15 per genotype) taken on 6/20/23
  File 5: Ley readings (15 per genotype) taken on 9/7/23
  Note: LICOR provides a data dictionary here

## Slide 6
Roadblocks/Risks | Mitigation
Missing/incomplete data due to weather/accidents/disease/etc. | Avoided ! 
Collaboration Misunderstanding | - Define goals clearly, provide background - Lots of discussions about what we are seeing, next steps, and motivation - Sharing next steps throughout the duration of the project
Shareability/Accessibility of the Code and Analysis | - Clearly document all steps (reference, methodology, commenting code) - Create R Shiny app for interactive visuals without coding experience - Use git, maintain proper file structure - Walkthrough of code, make Rmarkdown file and detailed README
Code Not be Useable on New Data | - Define a data input structure that we think is ideal for analysis going forward, and keep this defined structure - Keep everything standardized (choose gbs 088 or 88)
Low Prediction Accuracy | - Feature analysis to understand which are highest contributors - Talk about lessons learned, and improve this season's collection - Create general pipeline for smooth and easy LICOR ingestion in R

## Slide 7: Project Timeline
Data Collection and Information Gathering
Data Ingestion and Cleaning/Wrangling
Feature Engineering and Data Exploration
Training Models
Model Evaluation and Selection
✔️
Reevaluate and Retrain for improvement
Make predictions and share results
1. Ingest:
  - Read in the varying formats of the data, standardize dataset, and combine into clean structure
2. Clean/Wrangle:
  - Check/handle missing data or incorrect (hplc <50), add labels (FG/Ley, location in row, etc.)
3. Visualize:
  - Create interactive visuals to look at the cleaned data

## Slide 8: Project Status – March 25 II. Data Ingestion and Cleaning/Wrangling
Blocked
Understand HPLC Data Collection: Data collection process to generate HPLC? How much spread in SHU is expected for 1 genotype?
To Do
Read in LICOR data from all different formats
Clean LICOR Data
Add addition columns to LICOR and perform feature analysis
Combine LICOR with SHU and Visualize data
Completed
Setup GIT for project
Create excel file of HPLC data, add gbs/names, and then read into excel
Clean data: standardize column types, handle ”<“ , add shu labels
Plot hplc data, look for outliers/important behavior
In Progress
Design interactive app to look at the data - Build interactive app interface - Graphs of SHU per genotype - Anomaly/outlier graphs
Work with Ibrar and team to create standardized LICOR input for R Code